## Planilha Orcamentária
PLANILHA ORÇAMENTÁRIA DE CUSTOS
PREFEITURA MUNICIPAL DE PATROCÍNIO/MG |  |  |  |  | DATA: |  | 2023-06-29
OBRA: RECAPEAMENTO ASFÁLTICO EM CBUQ
LOCAIS: |  |  |  |  | FOLHA Nº: 01/05.
RUA EMYDIO DO ESPÍRITO SANTO – BAIRRO CONGONHAS;
RUA VEREADORA ISMENE MENDES – BAIRRO CONGONHAS;
RUA SEBASTIÃO ROGÉRIO – BAIRRO CRUZEIRO DA SERRA;
RUA ELPÍDIO RIBEIRO DA ROCHA – BAIRRO MORADA DO SOL;
RUA JOSÉ JACINTO – BAIRRO MORADA DO SOL;
RUA JOSÉ JACINTO CAMPOS – BAIRRO MORADA DO SOL;
RUA PROFESSOR JOÃO DE MELO – BAIRRO SANTA TEREZINHA;
RUA DOUTOR INFANTE VIEIRA – BAIRRO SÃO BENEDITO;
RUA ZEQUINHA SILVESTRE – BAIRRO SÃO BENEDITO;
RUA JOSÉ LUIZ DA SILVA – BAIRRO SÃO JUDAS;
RUA MIGUEL MARQUES – BAIRRO SÃO JUDAS;
RUA PROFESSOR JOÃO DE MELO – BAIRRO SÃO JUDAS.
FORMA DE EXECUÇÃO:
REGIÃO/MÊS DE REFERÊNCIA: SETOP/SEINFRA REGIÃO TRIÂNGULO E ALTO PARANAÍBA - JANEIRO DE 2023 - SEM DESNONERAÇÃO / SINAPI - MAIO/2023 - NÃO DESONERADO. |  |  |  |  | ( ) | DIRETA | ( X ) | INDIRETA
*DEMONSTRATIVO DE BDI EXTRAÍDO DA TABELA DE REFERÊNCIA (SETOP/SEINFRA) ACIMA RELACIONADA - PÁG. 15. | [6 empty] | ISS = 2% | 22.41%
ITEM | REFERÊNCIA | CÓDIGO | DESCRIÇÃO | UNIDADE | QUANTIDADE | PREÇO UNITÁRIO S/ BDI | PREÇO UNITÁRIO C/ BDI | PREÇO TOTAL
1.0 |  |  | INSTALAÇÕES INICIAIS DA OBRA |  |  |  |  | 1737.3
1.1 | SEINFRA | ED-28427 | FORNECIMENTO E COLOCAÇÃO DE PLACA DE OBRA EM CHAPA GALVANIZADA #26, ESP. 0,45MM, DIMENSÃO (3X1,5)M, PLOTADA COM ADESIVO VINÍLICO, AFIXADA COM REBITES 4,8X40MM, EM ESTRUTURA METÁLICA DE METALON 20X20MM, ESP. 1,25MM, INCLUSIVE SUPORTE EM EUCALIPTO AUTOCLAVADO PINTADO COM TINTA PVA DUAS (2) DEMÃOS | U | 1 | 1419.25 | 1737.3 | 1737.3
2.0 |  |  | MOBILIZAÇÃO E DESMOBILIZAÇÃO DE OBRA |  |  |  |  | 3804.1005
OBRAS EM CENTRO URBANO OU REGIÃO LIMÍTROFE - para obras executadas em centros urbanos ou próximos de centros urbanos
2.1 | SEINFRA | ED-50394 | MOBILIZAÇÃO E DESMOBILIZAÇÃO DE OBRA EM CENTRO URBANO OU REGIÃO LIMÍTROFE COM VALOR ACIMA DE 3.000.000,01 | % | 0.2 | 1553835.6589 | 1902050.23 | 3804.1005
3.0 |  |  | RECAPEAMENTO ASFÁLTICO EM CBUQ |  |  |  |  | 1481973.71
3.1 | SINAPI/MG | 99814 | LIMPEZA DE SUPERFÍCIE COM JATO DE ALTA PRESSÃO. AF_04/2019 | M² | 21908.64 | 1.77 | 2.17 | 47541.75
3.2 | SEINFRA | RO-51229 | PINTURA DE LIGAÇÃO (EXECUÇÃO E FORNECIMENTO DO MATERIAL BETUMINOSO, EXCLUSIVE TRANSPORTE DO MATERIAL BETUMINOSO) | M² | 20182.536 | 2.14 | 2.62 | 52878.24
3.3 | SEINFRA | RO-41376 | TRANSPORTE DE MATERIAL DE QUALQUER NATUREZA. DISTÂNCIA MÉDIA DE TRANSPORTE >= 50,10 KM | TXKM | 4006.2334 | 0.8 | 0.98 | 3926.11
3.4 | SEINFRA | ED-7623 | EXECUÇÃO E APLICAÇÃO DE CONCRETO BETUMINOSO USINADO A QUENTE (CBUQ), MASSA COMERCIAL, INCLUINDO FORNECIMENTO E TRANSPORTE DOS AGREGADOS E MATERIAL BETUMINOSO, EXCLUSIVE TRANSPORTE DA MASSA ASFÁLTICA ATÉ A PISTA | M³ | 706.3888 | 1570.58 | 1922.55 | 1358067.71
3.5 | SEINFRA | RO-14031 | TRANSPORTE DE CONCRETO BETUMINOSO USINADO A QUENTE. DISTÂNCIA MÉDIA DE TRANSPORTE <= 10,0 KM (VOLUME COMPACTADO) | M³XKM | 5015.3602 | 3.19 | 3.9 | 19559.9
4.0 |  |  | SERVIÇOS DE DRENAGEM PLUVIAL |  |  |  |  | 354803.96
4.1 | SEINFRA | ED-48492 | DEMOLIÇÃO MECANIZADA DE REVESTIMENTO ASFÁLTICO, COM EQUIPAMENTO PNEUMÁTICO, INCLUSIVE AFASTAMENTO E EMPILHAMENTO, EXCLUSIVE TRANSPORTE E RETIRADA DO MATERIAL DEMOLIDO | M² | 1726.104 | 9.35 | 11.45 | 19763.89
4.2 | SEINFRA | ED-51131 | CARGA MANUAL DE MATERIAL DE QUALQUER NATUREZA SOBRE CAMINHÃO, EXCLUSIVE TRANSPORTE | M³ | 51.7831 | 39.52 | 48.38 | 2505.27
4.3 | SEINFRA | ED-29231 | TRANSPORTE DE MATERIAL DE QUALQUER NATUREZA EM CAMINHÃO, DISTÂNCIA MAIOR QUE 2KM E MENOR OU IGUAL A 5KM, DENTRO DO PERÍMETRO URBANO, EXCLUSIVE CARGA, INCLUSIVE DESCARGA | M³XKM | 258.9156 | 3 | 3.67 | 950.22
4.4 | SINAPI/MG | 94287 | EXECUÇÃO DE SARJETA DE CONCRETO USINADO, MOLDADA IN LOCO EM TRECHO RETO, 30 CM BASE X 10 CM ALTURA. AF_06/2016 | M | 5753.68 | 47.08 | 57.63 | 331584.58
5.0 |  |  | OBRAS COMPLEMENTARES |  |  |  |  | 48064.08
5.1 | SEINFRA | ED-51148 | RAMPA PARA ACESSO DE DEFICIENTE, EM CONCRETO SIMPLES FCK = 25 MPA, DESEMPENADA, COM PINTURA INDICATIVA, 02 DEMÃOS | U | 94 | 417.71 | 511.32 | 48064.08
6.0 |  |  | ADMINISTRAÇÃO LOCAL |  |  |  |  | 15471.18
6.1 | SEINFRA | COMP. 01 | ADMINISTRAÇÃO LOCAL | MÊS | 3 | 4212.9409 | 5157.06 | 15471.18
TOTAL GERAL DA OBRA | [7 empty] | 1905854.3305
Edson José De Souza Neto
ENGENHEIRO CIVIL - CREA Nº 40.612/D
Engenheiro Civil - CREA/MG nº: 108.997/D
Deiró Moreira Marra
Prefeito Municipal de Patrocínio
ESTADO DE MINAS GERAIS
Secretaria de Estado de Infraestrutura, Mobilidade e Parcerias
Subsecretaria de Obras e Infraestrutura
Superintendência de Obras Públicas
Diretoria de Engenharia e Qualidade

## Memória de Cálculo
MEMÓRIA DE CÁLCULO DE QUANTITATIVOS
PREFEITURA MUNICIPAL DE PATROCÍNIO/MG |  |  |  |  | FOLHA Nº: 04/05.
OBRA: RECAPEAMENTO ASFÁLTICO EM CBUQ |  |  |  |  | DATA: | 2023-06-29
LOCAIS:
RUA EMYDIO DO ESPÍRITO SANTO – BAIRRO CONGONHAS;
RUA VEREADORA ISMENE MENDES – BAIRRO CONGONHAS;
RUA SEBASTIÃO ROGÉRIO – BAIRRO CRUZEIRO DA SERRA;
RUA ELPÍDIO RIBEIRO DA ROCHA – BAIRRO MORADA DO SOL;
RUA JOSÉ JACINTO – BAIRRO MORADA DO SOL;
RUA JOSÉ JACINTO CAMPOS – BAIRRO MORADA DO SOL;
RUA PROFESSOR JOÃO DE MELO – BAIRRO SANTA TEREZINHA;
RUA DOUTOR INFANTE VIEIRA – BAIRRO SÃO BENEDITO;
RUA ZEQUINHA SILVESTRE – BAIRRO SÃO BENEDITO;
RUA JOSÉ LUIZ DA SILVA – BAIRRO SÃO JUDAS;
RUA MIGUEL MARQUES – BAIRRO SÃO JUDAS;
RUA PROFESSOR JOÃO DE MELO – BAIRRO SÃO JUDAS.
ITEM | CÓDIGO | DESCRIÇÃO | UNIDADE | QUANTIDADE | MEMÓRIA
1.0 |  | INSTALAÇÕES INICIAIS DA OBRA
1.1 | ED-28427 | FORNECIMENTO E COLOCAÇÃO DE PLACA DE OBRA EM CHAPA GALVANIZADA #26, ESP. 0,45MM, DIMENSÃO (3X1,5)M, PLOTADA COM ADESIVO VINÍLICO, AFIXADA COM REBITES 4,8X40MM, EM ESTRUTURA METÁLICA DE METALON 20X20MM, ESP. 1,25MM, INCLUSIVE SUPORTE EM EUCALIPTO AUTOCLAVADO PINTADO COM TINTA PVA DUAS (2) DEMÃOS | U | 1 | Conforme padrão SEINFRA
2.0 |  | MOBILIZAÇÃO E DESMOBILIZAÇÃO DE OBRA
2.1 | ED-50394 | MOBILIZAÇÃO E DESMOBILIZAÇÃO DE OBRA EM CENTRO URBANO OU REGIÃO LIMÍTROFE COM VALOR ACIMA DE 3.000.000,01 | % | 0.2 | VALOR DA OBRA S/ BDI (SEM O VALOR DE MOB. E DESM. | VALOR DA OBRA C/ BDI (SEM O VALOR DE MOB. E DESM. |  | VALOR DE MOB. E DESM. C/BDI (VALOR DA OBRA C/BDI SEM O VALOR DO ITEM MO. E DESM.) / 100 * % do código do item
[5 empty] | 1553835.6589 | 1902050.23 |  | 3804.1005
3.0 |  | RECAPEAMENTO ASFÁLTICO EM CBUQ
3.1 | 99814 | LIMPEZA DE SUPERFÍCIE COM JATO DE ALTA PRESSÃO. AF_04/2019
VIAS |  | *Área de recapeamento/pista de rolamento extraída do projeto por meio do software AutoCAD | Área total (m²)
BAIRRO CONGONHAS
RUA EMYDIO DO ESPÍRITO SANTO – BAIRRO CONGONHAS; |  |  | 1376.74
RUA VEREADORA ISMENE MENDES – BAIRRO CONGONHAS; |  |  | 1764.6
Área total de recapeamento no bairro (m²) |  |  | 3141.34
BAIRRO CRUZEIRO DA SERRA
RUA SEBASTIÃO ROGÉRIO – BAIRRO CRUZEIRO DA SERRA; |  |  | 2459.52
Área total de recapeamento no bairro (m²) |  |  | 2459.52
BAIRRO MORADA DO SOL
RUA ELPÍDIO RIBEIRO DA ROCHA – BAIRRO MORADA DO SOL; |  |  | 3155.57
RUA JOSÉ JACINTO – BAIRRO MORADA DO SOL; |  |  | 624.3
RUA JOSÉ JACINTO CAMPOS – BAIRRO MORADA DO SOL; |  |  | 536.46
Área total de recapeamento no bairro (m²) |  |  | 4316.33
BAIRRO SANTA TEREZINHA
RUA PROFESSOR JOÃO DE MELO – BAIRRO SANTA TEREZINHA; |  |  | 2399.36
Área total de recapeamento no bairro (m²) |  |  | 2399.36
BAIRRO SÃO BENEDITO
RUA DOUTOR INFANTE VIEIRA – BAIRRO SÃO BENEDITO; |  |  | 1884.64
RUA ZEQUINHA SILVESTRE – BAIRRO SÃO BENEDITO; |  |  | 1850.41
Área total de recapeamento no bairro (m²) |  |  | 3735.05
BAIRRO SÃO JUDAS
RUA JOSÉ LUIZ DA SILVA – BAIRRO SÃO JUDAS; |  |  | 1814.56
RUA MIGUEL MARQUES – BAIRRO SÃO JUDAS; |  |  | 1965.34
RUA PROFESSOR JOÃO DE MELO – BAIRRO SÃO JUDAS. |  |  | 2077.14
Área total de recapeamento no bairro (m²) |  |  | 5857.04
ÁREA TOTAL DE LIMPEZA/RECAPEAMENTO: |  |  | 21908.64
3.2 | RO-51229 | PINTURA DE LIGAÇÃO (EXECUÇÃO E FORNECIMENTO DO MATERIAL BETUMINOSO, EXCLUSIVE TRANSPORTE DO MATERIAL BETUMINOSO) | M² | 20182.536 | *Conforme área total evidenciada no item acima subtraído as áreas de sarjetas (20.182,54 - 1.726,10)
3.3 | RO-41376 | TRANSPORTE DE MATERIAL DE QUALQUER NATUREZA. DISTÂNCIA MÉDIA DE TRANSPORTE >= 50,10 KM | TXKM | 4006.2334 | Área de Recapeamento: (m²) |  | DMT (km): | Índice de Consumo (RR-2C) (t/m²): | Total (TxKM):
[5 empty] | 20182.536 |  | 397 | 0.0005 | 4006.2334
3.4 | ED-7623 | EXECUÇÃO E APLICAÇÃO DE CONCRETO BETUMINOSO USINADO A QUENTE (CBUQ), MASSA COMERCIAL, INCLUINDO FORNECIMENTO E TRANSPORTE DOS AGREGADOS E MATERIAL BETUMINOSO, EXCLUSIVE TRANSPORTE DA MASSA ASFÁLTICA ATÉ A PISTA | M³ | 706.3888 | Área de Recapeamento: (m²) |  |  | Espessura do CBUQ (m): | Total (M³):
[5 empty] | 20182.536 |  |  | 0.035 | 706.3888
3.5 | RO-14031 | TRANSPORTE DE CONCRETO BETUMINOSO USINADO A QUENTE. DISTÂNCIA MÉDIA DE TRANSPORTE <= 10,0 KM (VOLUME COMPACTADO) | M³XKM | 5015.3602 | Volume do CBUQ (m³) |  | DMT (km): |  | Total (M³xKM):
[5 empty] | 706.3888 |  | 7.1 |  | 5015.3602
4.0 |  | SERVIÇOS DE DRENAGEM PLUVIAL
LEVANTAMENTO SARJETAS E RAMPAS
VIAS |  | Cotas (sarjetas) | Extensáo total (sarjetas) | Larg. das sarjetas existentes a demolir | Área de domolição de sarjetas | Rampas de acessibilidade
BAIRRO CONGONHAS | [9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RUA EMYDIO DO ESPÍRITO SANTO – BAIRRO CONGONHAS; |  | (71,25+79,56+113,91+119,75) | 384.47 | 0.3 | 115.341 | 6
RUA VEREADORA ISMENE MENDES – BAIRRO CONGONHAS; |  | (138,16+136,67+40,29+41,04+63,41+68,23) | 487.8 | 0.3 | 146.34 | 6
BAIRRO CRUZEIRO DA SERRA
RUA SEBASTIÃO ROGÉRIO – BAIRRO CRUZEIRO DA SERRA; |  | (160,50+156,95+158,79+157,11+34,25+35,74) | 703.34 | 0.3 | 211.002 | 10
BAIRRO MORADA DO SOL
RUA ELPÍDIO RIBEIRO DA ROCHA – BAIRRO MORADA DO SOL; |  | (131,68+110,00+187,14+456,82) | 885.64 | 0.3 | 265.692 | 6
RUA JOSÉ JACINTO – BAIRRO MORADA DO SOL; |  | (81,05+82,18+2,64+2,04) | 167.91 | 0.3 | 50.373 | 4
RUA JOSÉ JACINTO CAMPOS – BAIRRO MORADA DO SOL; |  | (72,14+70,35+2,49+2,97) | 147.95 | 0.3 | 44.385 | 4
BAIRRO SANTA TEREZINHA
RUA PROFESSOR JOÃO DE MELO – BAIRRO SANTA TEREZINHA; |  | (62,61+59,69+51,16+52,68+55,25+56,33+56,37+56,26+59,97+61,22) | 571.54 | 0.3 | 171.462 | 20
BAIRRO SÃO BENEDITO
RUA DOUTOR INFANTE VIEIRA – BAIRRO SÃO BENEDITO; |  | (120,35+121,18+129,45+129,08) | 500.06 | 0.3 | 150.018 | 8
RUA ZEQUINHA SILVESTRE – BAIRRO SÃO BENEDITO; |  | (123,08+123,12+128,35+128,04) | 502.59 | 0.3 | 150.777 | 8
BAIRRO SÃO JUDAS
RUA JOSÉ LUIZ DA SILVA – BAIRRO SÃO JUDAS; |  | (99,34+97,94+143,69+143,97) | 484.94 | 0.3 | 145.482 | 8
RUA MIGUEL MARQUES – BAIRRO SÃO JUDAS; |  | (86,54+84,89+148,85+150,21) | 470.49 | 0.3 | 141.147 | 8
RUA PROFESSOR JOÃO DE MELO – BAIRRO SÃO JUDAS. |  | (56,41+161,07+229,47) | 446.95 | 0.3 | 134.085 | 6
|  | Extensão total de sarjetas: | 5753.68
|  |  | Área total de domolição de sarjetas: |  | 1726.104
[5 empty] | Total (rampas): | 94
4.1 | ED-48492 | DEMOLIÇÃO MECANIZADA DE REVESTIMENTO ASFÁLTICO, COM EQUIPAMENTO PNEUMÁTICO, INCLUSIVE AFASTAMENTO E EMPILHAMENTO, EXCLUSIVE TRANSPORTE E RETIRADA DO MATERIAL DEMOLIDO
Conforme levantamento acima:
Área total de domolição de sarjetas: |  | 1726.104
4.2 | ED-51131 | CARGA MANUAL DE MATERIAL DE QUALQUER NATUREZA SOBRE CAMINHÃO, EXCLUSIVE TRANSPORTE
Conforme levantamento acima:
Área total de domolição de sarjetas: |  | 1726.104
Espessura a demolir: |  | 0.03
Volume/carga: |  | 51.7831
4.3 | ED-29231 | TRANSPORTE DE MATERIAL DE QUALQUER NATUREZA EM CAMINHÃO, DISTÂNCIA MAIOR QUE 2KM E MENOR OU IGUAL A 5KM, DENTRO DO PERÍMETRO URBANO, EXCLUSIVE CARGA, INCLUSIVE DESCARGA
Conforme levantamento acima:
Área total de domolição de sarjetas: |  | 1726.104
Espessura a demolir: |  | 0.03
D.M.T.: |  | 5
Volume/carga: |  | 258.9156
4.4 | 94287 | EXECUÇÃO DE SARJETA DE CONCRETO USINADO, MOLDADA IN LOCO EM TRECHO RETO, 30 CM BASE X 10 CM ALTURA. AF_06/2016
Conforme levantamento acima:
Extensão total de sarjetas: |  | 5753.68
5.0 |  | OBRAS COMPLEMENTARES
5.1 | ED-51148 | RAMPA PARA ACESSO DE DEFICIENTE, EM CONCRETO SIMPLES FCK = 25 MPA, DESEMPENADA, COM PINTURA INDICATIVA, 02 DEMÃOS
Conforme levantamento acima:
Total (rampas): |  | 94
6.0 |  | ADMINISTRAÇÃO LOCAL
6.1 | COMP. 01 | ENGENHEIRO CIVIL DE OBRA JÚNIOR COM ENCARGOS COMPLEMENTARES | 3 meses | 0.090909 | 1hora*5dias*4semanas = 20 horas/220 horas = 0,090909 / mês
|  | ENCARREGADO GERAL DE OBRAS COM ENCARGOS COMPLEMENTARES | 3 meses | 0.27273 | 3horas*5dias*4semanas = 60 horas/220 horas = 0,272727 / mês
Edson José De Souza Neto
Engenheiro Civil - CREA/MG nº: 108.997/D
Deiró Moreira Marra
Prefeito Municipal de Patrocínio
ESTADO DE MINAS GERAIS
Secretaria de Estado de Infraestrutura, Mobilidade e Parcerias
Subsecretaria de Obras e Infraestrutura
Superintendência de Obras Públicas
Diretoria de Engenharia e Qualidade

## COMP. 01
COMPOSIÇÃO DE CUSTO UNITÁRIO | [5 empty] | DATA: | 2023-06-29
FOLHA Nº: 03/05.
COMP. 01 |  | DESCRIÇÃO DO SERVIÇO | UNIDADE |  | FONTE |  | PREÇO REFERENCIAL
|  | ADMINISTRAÇÃO LOCAL | MÊS |  | SETOP/SEINFRA REGIÃO TRIÂNGULO E ALTO PARANAÍBA - JANEIRO DE 2023 - SEM DESNONERAÇÃO |  | 4212.9409
TABELA | CÓDIGO | DESCRIÇÃO DO INSUMO | UNIDADE | FÓRMULA/CÁLCULO | COEFICIENTE | CUSTO UNITÁRIO | CUSTO TOTAL
SEINFRA | ED-21769 | ENGENHEIRO CIVIL DE OBRA JÚNIOR COM ENCARGOS COMPLEMENTARES | MÊS | 1hora*5dias*4semanas = 20 horas/220 horas = 0,090909 / mês | 0.090909 | 19811.82 | 1801.0745
SEINFRA | ED-21776 | ENCARREGADO GERAL DE OBRAS COM ENCARGOS COMPLEMENTARES | MÊS | 3horas*5dias*4semanas = 60 horas/220 horas = 0,272727 / mês | 0.27273 | 8843.51 | 2411.8664
[6 empty] | PATROCÍNIO, | 2023-06-29
Edson José De Souza Neto
Engenheiro Civil - CREA/MG nº: 108.997/D
Deiró Moreira Marra
Prefeito Municipal de Patrocínio

## BDI
DEMONSTRATIVO DO BDI - SEM DESONERAÇÃO - OBRA RODOVIÁRIA
BDI (CONFORME ACÓRDÃO Nº 2622/13 e LEI Nº 13.161 DE 31/08/15)
DISCRIMINAÇÃO DAS PARCELAS | SIG. (1) | CONSTRUÇÃO DE RODOVIAS E FERROVIAS | [6 empty] | INC. (6)
|  | ISS (2) |  |  |  | DIFERENCIADO
|  | 2% | 3% | 4% | 5% | MATERIAL (5) | SERVIÇO TERCEIRIZADO (4) (ISS=5%) | EQUIPAMENTO (3) (ISS=5%)
CUSTO DIRETO | CD | 100% | 100% | 100% | 100% | 100% | 100% | 100%
ADMINISTRAÇÃO CENTRAL | AC | 4.67% | 4.67% | 4.67% | 4.67% | 3.42% | 4.01% | 3.42% | CD
LUCRO BRUTO | L | 7.53% | 7.53% | 7.53% | 7.53% | 4.94% | 6.64% | 4.94% | CD
DESPESAS FINANCEIRAS | DF | 0.9647% | 0.9647% | 0.9647% | 0.9647% | 0.9647% | 0.9647% | 0.9647% | CD
SEGUROS, GARANTIAS E RISCO |  | 1.71% | 1.71% | 1.71% | 1.71% | 1.3% | 0.82% | 1.3% | CD
SEGUROS + GARANTIAS | S | 0.74% | 0.74% | 0.74% | 0.74% | 0.53% | 0.32% | 0.53% | CD
RISCO(*) | R | 0.97% | 0.97% | 0.97% | 0.97% | 0.77% | 0.5% | 0.77% | CD
TRIBUTOS | I | 5.65% | 6.65% | 7.65% | 8.65% | 3.65% | 5.65% | 5.65% | PV
ISS | ISS(2) | 2% | 3% | 4% | 5% | - | 2% | 2% | PV
PIS | PIS | 0.65% | 0.65% | 0.65% | 0.65% | 0.65% | 0.65% | 0.65% | PV
COFINS | - | 3% | 3% | 3% | 3% | 3% | 3% | 3% | PV
CPRB | INSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PV
FÓRMULA DO BDI |  | (1 + (AC + S + G + R)) x (1 + DF) x (1 + L)
(1 - (I + CPRB))
BDI (NUMERADOR) |  | 15.49% | 15.49% | 15.49% | 15.49% | 10.95% | 12.87% | 10.95%
BDI (DENOMINADOR) |  | 94.35% | 93.35% | 92.35% | 91.35% | 96.35% | 94.35% | 94.35%
BDI |  | 22.41% | 23.72% | 25.06% | 26.43% | 15.16% | 19.63% | 17.6%
OBSERVAÇÕES
(1) SIGLA. (2) INCIDÊNCIA DE ISS EM 100% DO PREÇO DE VENDA, COM PERCENTUAIS DE 2%, CONFORME LEGISLAÇÃO MUNICIPAL. (3) BDI DIFERENCIADO A SER APLICADO EM LOCAÇÃO DE CUSTO HORÁRIO DE EQUIPAMENTO. (4) BDI DIFERENCIADO A SER APLICADO PARA SERVIÇOS TERCEIRIZADOS. (5) BDI DIFERENCIADO A SER APLICADO PARA FORNECIMENTO DE MATERIAL BETUMINOSO E MATERIAL DE JAZIDA. (6) INCIDÊNCIA.
Patrocínio, |  | 2023-06-29 |  |  | FOLHA Nº: 02/05.
Edson José De Souza Neto
Engenheiro Civil - CREA/MG nº: 108.997/D
Deiró Moreira Marra
Prefeito Municipal de Patrocínio

## Cronograma F.F
CRONOGRAMA FÍSICO-FINANCEIRO
PREFEITURA MUNICIPAL DE PATROCÍNIO/MG |  | VALOR TOTAL DO CONVÊNIO: |  | 1905854.3305
OBRA: RECAPEAMENTO ASFÁLTICO EM CBUQ |  | FOLHA Nº: 05/05. |  | DATA: | 2023-06-29
LOCAIS:
RUA EMYDIO DO ESPÍRITO SANTO – BAIRRO CONGONHAS;
RUA VEREADORA ISMENE MENDES – BAIRRO CONGONHAS;
#REF!
RUA SEBASTIÃO ROGÉRIO – BAIRRO CRUZEIRO DA SERRA;
RUA ELPÍDIO RIBEIRO DA ROCHA – BAIRRO MORADA DO SOL;
RUA JOSÉ JACINTO – BAIRRO MORADA DO SOL;
RUA JOSÉ JACINTO CAMPOS – BAIRRO MORADA DO SOL;
RUA PROFESSOR JOÃO DE MELO – BAIRRO SANTA TEREZINHA;
RUA DOUTOR INFANTE VIEIRA – BAIRRO SÃO BENEDITO;
RUA ZEQUINHA SILVESTRE – BAIRRO SÃO BENEDITO;
RUA JOSÉ LUIZ DA SILVA – BAIRRO SÃO JUDAS;
RUA MIGUEL MARQUES – BAIRRO SÃO JUDAS;
RUA PROFESSOR JOÃO DE MELO – BAIRRO SÃO JUDAS.
PRAZO PREVISTO DE EXECUÇÃO DAS OBRAS: 3 MESES
ITEM | ETAPAS/DESCRIÇÃO | FÍSICO/ FINANCEIRO | TOTAL ETAPAS | MÊS 1 | MÊS 2 | MÊS 3
1.0 | INSTALAÇÕES INICIAIS DA OBRA | Físico % | 0.09116% | 100% | 0% | 0%
|  | Financeiro | 1737.3 | 1737.3 | 0 | 0
2.0 | MOBILIZAÇÃO E DESMOBILIZAÇÃO DE OBRA | Físico % | 0.1996% | 50% | 0% | 50%
|  | Financeiro | 3804.1005 | 1902.0502 | 0 | 1902.0502
3.0 | RECAPEAMENTO ASFÁLTICO EM CBUQ | Físico % | 77.76% | 30% | 35% | 35%
|  | Financeiro | 1481973.71 | 444592.113 | 518690.7985 | 518690.7985
4.0 | SERVIÇOS DE DRENAGEM PLUVIAL | Físico % | 18.62% | 30% | 35% | 35%
|  | Financeiro | 354803.96 | 106441.188 | 124181.386 | 124181.386
5.0 | OBRAS COMPLEMENTARES | Físico % | 2.522% | 30% | 35% | 35%
|  | Financeiro | 48064.08 | 14419.224 | 16822.428 | 16822.428
6.0 | ADMINISTRAÇÃO LOCAL | Físico % | 0.8118% | 30% | 35% | 35%
|  | Financeiro | 15471.18 | 4641.354 | 5414.913 | 5414.913
TOTAL |  | Físico % | 100% | 30.1% | 34.9% | 35%
|  | Financeiro | 1905854.3305 | 573733.2292 | 665109.5255 | 667011.5757
__________________________________________________
Edson José De Souza Neto
Engenheiro Civil - CREA/MG nº: 108.997/D
__________________________________________________
Deiró Moreira Marra
Prefeito Municipal de Patrocínio
ESTADO DE MINAS GERAIS
Secretaria de Estado de Infraestrutura, Mobilidade e Parcerias
Subsecretaria de Obras e Infraestrutura
Superintendência de Obras Públicas
Diretoria de Engenharia e Qualidade

## Cronograma Global
CRONOGRAMA FÍSICO-FINANCEIRO
PREFEITURA MUNICIPAL DE PATROCÍNIO/MG |  | VALOR TOTAL DO CONVÊNIO: |  | 4358020.143
OBRA: RECAPEAMENTO ASFÁLTICO EM CBUQ |  | FOLHA Nº: 01/01. |  | DATA: | 2023-06-29
LOCAIS:
RUA NHONHÔ PAIVA – BAIRRO MARCIANO BRANDÃO;
RUA DR. VICENTE SOARES – BAIRRO MARCIANO BRANDÃO;
RUA GERVÁSIO MARQUES – BAIRRO MATINHA;
RUA MANOEL DAMAS – BAIRRO MATINHA;
ALAMEDA DOS ÁLAMOS – BAIRRO MORADA NOVA;
ALAMEDA DOS CEDROS – BAIRRO MORADA NOVA;
RUA CECÍLIA PEREZ – BAIRRO SANTO ANTÔNIO;
RUA CORONEL JOSÉ FELICIANO – BAIRRO SANTO ANTÔNIO;
RUA FURTADO DE MENEZES – BAIRRO SANTO ANTÔNIO;
RUA JOAQUIM COELHO MARRA – BAIRRO SANTO ANTÔNIO;
RUA ORLANDO FERNANDES BOTELHO – BAIRRO SANTO ANTÔNIO;
RUA MAJOR TOBIAS MACHADO – BAIRRO SANTO ANTÔNIO;
RUA PROFESSOR OSCAR RODARTE – BAIRRO SÃO FRANCISCO;
RUA SALITRE – BAIRRO SÃO VICENTE.
RUA EMYDIO DO ESPÍRITO SANTO – BAIRRO CONGONHAS;
RUA VEREADORA ISMENE MENDES – BAIRRO CONGONHAS;
RUA SEBASTIÃO ROGÉRIO – BAIRRO CRUZEIRO DA SERRA;
RUA ELPÍDIO RIBEIRO DA ROCHA – BAIRRO MORADA DO SOL;
RUA JOSÉ JACINTO – BAIRRO MORADA DO SOL;
RUA JOSÉ JACINTO CAMPOS – BAIRRO MORADA DO SOL;
RUA PROFESSOR JOÃO DE MELO – BAIRRO SANTA TEREZINHA;
RUA DOUTOR INFANTE VIEIRA – BAIRRO SÃO BENEDITO;
RUA ZEQUINHA SILVESTRE – BAIRRO SÃO BENEDITO;
RUA JOSÉ LUIZ DA SILVA – BAIRRO SÃO JUDAS;
RUA MIGUEL MARQUES – BAIRRO SÃO JUDAS;
RUA PROFESSOR JOÃO DE MELO – BAIRRO SÃO JUDAS.
PRAZO PREVISTO DE EXECUÇÃO DAS OBRAS: 3 MESES
ITEM | ETAPAS/DESCRIÇÃO | FÍSICO/ FINANCEIRO | TOTAL ETAPAS | MÊS 1 | MÊS 2 | MÊS 3
1.0 | INSTALAÇÕES INICIAIS DA OBRA | Físico % | 0.07973% | 100% | 0% | 0%
|  | Financeiro | 3474.6 | 3474.6 | 0 | 0
2.0 | MOBILIZAÇÃO E DESMOBILIZAÇÃO DE OBRA | Físico % | 0.1996% | 50% | 0% | 50%
|  | Financeiro | 8698.643 | 4349.3215 | 0 | 4349.3215
3.0 | RECAPEAMENTO ASFÁLTICO EM CBUQ | Físico % | 77.9% | 30% | 35% | 35%
|  | Financeiro | 3395104.47 | 1018531.341 | 1188286.5645 | 1188286.5645
4.0 | SERVIÇOS DE DRENAGEM PLUVIAL | Físico % | 18.45% | 30% | 35% | 35%
|  | Financeiro | 804241.75 | 241272.525 | 281484.6125 | 281484.6125
5.0 | OBRAS COMPLEMENTARES | Físico % | 2.652% | 30% | 35% | 35%
|  | Financeiro | 115558.32 | 34667.496 | 40445.412 | 40445.412
6.0 | ADMINISTRAÇÃO LOCAL | Físico % | 0.71% | 30% | 35% | 35%
|  | Financeiro | 30942.36 | 9282.708 | 10829.826 | 10829.826
TOTAL |  | Físico % | 100% | 30.1% | 34.9% | 35%
|  | Financeiro | 4358020.143 | 1311577.9915 | 1521046.415 | 1525395.7365
__________________________________________________
Edson José De Souza Neto
Engenheiro Civil - CREA/MG nº: 108.997/D
__________________________________________________
Deiró Moreira Marra
Prefeito Municipal de Patrocínio
ESTADO DE MINAS GERAIS
Secretaria de Estado de Infraestrutura, Mobilidade e Parcerias
Subsecretaria de Obras e Infraestrutura
Superintendência de Obras Públicas
Diretoria de Engenharia e Qualidade